## UC
TAG | Feature | Use case | Customer | Admin | Sale | Marketing | Expert | Use case description
UC-1 | User Access | Create Account Registration | O |  | O | O | O | As a Customer, I want to Register a New Account, So that I can access the features and benefits offered by the platform. As a Customer, I want to login with another flatform account, So that i can access easy
UC-2 | User Access | View Course Details | O |  |  |  |  | As a Customer, I want to view the details of a specific course, So that I can gather information about the course, its content, and requirements.
UC-3 | System Admin | View Course List |  | O |  |  | O | As a Admin, I want to be able to view both published and unpublished courses, So that I can see the complete list of available courses and make informed decisions on which courses to explore.
UC-4 | User Access | View Saved Blogs | O |  |  |  |  | As a User, I want to be able to view my saved blogs, So that I can easily access and revisit the blogs that I found interesting or useful in the past.
UC-5 | System Admin | Course Edit |  | O |  |  | O | As a Admin, I want to be able to edit the details of a course, So that I can update and modify the course information to provide accurate and relevant content to the users. As a Admin, I want to add or delete chapters in a course, So that I can organize the course content in a structured manner and make necessary adjustments based on the course requirements. As a Admin, I want to add or delete target,audience details for a course, So that I can specify the intended audience and ensure the course aligns with their needs and skill levels. As a Admin, I want to add or delete course requirements, So that I can specify any prerequisites or recommended skills that users should possess before enrolling in the course.
UC-6 | System Admin | Lesson Edit |  | O |  |  | O | As a Admin, I want to see the list lesson, So that, I can management the lesson we have As a Admin, I want to delete the lesson, So that, I can remove the lesson not unnecessary
UC-7 | System Admin | Chapter Edit |  | O |  |  | O | As a Admin, I want to add or delete lessons within a chapter, So that I can modify the chapter structure and adjust the lesson order or content as needed.
UC-8 | User Access | Doing Feedback Lesson | O |  |  |  |  | As a Customer, I want to view a survey related to a lesson, So that I can provide my feedback and opinions on the lesson content and quality.
UC-9 | User Access | Answer the Survey | O |  |  |  |  | As a Customer, I want to answer the survey related to a lesson, So that I can provide my valuable input and contribute to improving the lesson and overall learning experience.
UC-10 | System Admin | Course Route Management |  | O |  |  |  | As an admin , I want to manage the content . So I created a common management page
UC-11 | System Admin | View Program List |  | O |  |  |  | As an admin , I want to manage the learning curve . So I've created a page that lists learning routes
UC-12 | User Access | Public Programs | O | O | O | O | O | As a customer , I would like to see what the learning curve has . so I clicked on the page's learning curve to see it
UC-13 | User Access | View Public Program Details | O | O | O | O | O | As a customer, I'd like to see what the curriculum vitae has. so I clicked on the learning path of the page to detail each course table of contents
UC-14 | System Admin | Add/Delete/Edit Program |  | O |  |  |  | As an admin , I can add edit and delete any course . so I created this page for that purpose
UC-15 | System Admin | Add/Delete/Edit Program Details |  | O |  |  |  | As an admin, I can add, edit and delete any course table of contents. so I created this page for that purpose
UC-16 | System Admin | View Program details List |  | O |  |  |  | As an admin , I want to manage the learning curve . So I've created a page that lists learning routes item
UC-17 | User Access | View Home Page | O |  |  |  |  | As a customer, I want to overview the f8 web. So that, I can choose the properly course to learn.
UC-18 | User Access | View Public Courses | O |  |  |  |  | As a customer, I want to view all public courses. So that, I can choose the properly course to learn.
UC-19 | User Access | Blog Details | O |  |  |  |  | As a Customer, I want to add/edit Blog. So that, I can write a blog and post it on forum.
UC-20 | User Access | View Blog List | O |  |  |  |  | As a Customer, I want to see a list of Blogs that have been posted on the forum. So that, I can choose a blog to read.
UC-21 | User Access | My Courses | O |  |  |  |  | As a Customer, I want to see a list of Courses Which I have registered. So that, I can go to the course and learn it.
UC-22 | System Admin | View Question List |  | O |  |  | O | As an Admin, I want to see a list of Questions. So that, I can choose properly questions for quizzes.
UC-23 | System Admin | Question Details |  | O |  |  | O | As an Admin, I want to add/edit a question. So that, I can modify properly content to the question.
UC-24 | User Access | Question Details | O |  |  |  |  | As a Customer, I want to take a quiz. So that, I can study better.
UC-25 | System Admin | View List Quiz |  | O |  |  | O | As an Admin, I want to see a list of Quizzes. So that, I can choose properly quiz and set it to a course.
UC-26 | System Admin | Edit Quiz |  | O |  |  | O | As an Admin, I want to edit a quiz. So that, I can choose a list of Questions and set it into a quiz.
UC-27 | User Access | View Profile | O | O | O | O | O | As a User, I want to view my profile. So that, I can access My profile to see it.
UC-28 | User Access | Edit Information | O | O | O | O | O | As a Customer, I want to edit my personal information. So that, I can access the Setting to edit.
UC-29 | System Admin | User Management |  | O |  |  |  | As an Admin, I want to update the user's role on the system. So that, I can access User List to update.
UC-30 | User Access | View My Blog List | O | O | O | O | O | As a User, I want to view my blog. So that, I can access My Blog to see it.
UC-31 | User Access | View Blog Detail | O | O | O | O | O | As a Marketing, I want to view blog detail. So that, I can click on the title of the blog to see it.
UC-32 | User Access | Cancel Order | O | O | O | O | O | As a User, I want to cancel my order. So that, I can go to the Setting, then Access My Order to cancel the order.
UC-33 | User Access | Answer the question | O | O | O | O | O | As an Expert, I want to answer the User question in each lesson. So that, I can access Q&A of the lesson to answer.
UC-34 | System Admin | Manage comments |  | O |  |  |  | As an Admin, I want to hide the comments of Users in the blog. So that, I can access the Comment List to hide comments.
UC-35 | User Access | See Video Lesson | O |  |  |  |  | As a Customer, I want to watch a video lesson, So that I can learn and understand the course content through visual and auditory means. As a Customer, I want to note in the video lesson, So that i can dont forget some information i was note
UC-36 | System Admin | Manage blog |  | O |  |  |  | As an Admin, I want to hide the blog of Users . So that, I can access the Blog List to hide comments. As a Admin, I want to find the blog was hide. So that, I can to be able to categorize the group of people who post violations
UC-37 | System Admin | Edit Lesson Detail |  | O |  |  |  | As a Admin, I want to edit the details of the courses. So that, I can add video links or categorize lessons. As a Admin, I want to edit the lesson of one chapter to another. So that, I can handle the lessons more easily
UC-38
UC-39
UC-40

## Product
# | Feature | Screen/Function | Planned | Actual | Quiz zing WF | Program Training WF | Screen/Function Details | In Charge | Status | SRS | SDS | Updated | Update Details
2 | User Access | Reset password | iter1 | iter1 |  |  | help users to reset their password | DatNTHE161924 | Done | II.1.i |  | not yet
3 | User Access | Change password | iter1 | iter1 |  |  | enable users to change their password | DatNTHE161924 | Done | II.1.h |  | not yet
4 | User Access | User Profile | iter1 | iter1 |  |  | - Allows users to view user profiles, review activities and courses. - Allow updating cover photo | DungDTHE163862 | Done | II.1.d |  | iter4 | Đã thêm hoạt động gần đây của người dùng.
5 | User Access | Settings Account Details | iter1 | iter1 |  |  | - Allows users to update avt, personal information | DungDTHE163862 | Done | II.1.e |  | not yet
6 | System Admin | User List | iter1 | iter1 |  |  | - Filter - Update actor - Delete User | DungDTHE163863 | Done | II.2.a |  | iter4 | - Filter đã chuyển thành combo box, đã show toast khi update thành công, đã thêm search, paging
7 | User Access | Home page | iter1 | iter1 |  |  | - View proCourse, course - Search course - Show notification | Daitvhe161138 | Done | II.1.f |  | not yet
8 | System Admin | New course | iter1 | iter1 | x |  | - New course | Daitvhe161138 | Done | II.2.b |  | not yet
9 | User Access | Public Courses | iter1 | iter1 |  |  | - List course - Search course | Daitvhe161138 | Done | II.1.g |  | not yet
10 | User Access | User Register | iter1 | iter1 |  |  | - New Account | TriLMHE163206 | Done | II.1.b |  | iter4 | - Sửa đăng nhập google, facebook, github luôn, - hiện fields khi lỗi, - check email đã tồn tại chưa, check phone đã tồn tại chưa mới gửi
11 | User Access | Course Details | iter1 | iter1 |  |  | - Show course detail | TriLMHE163206 | Done | II.1.c |  | iter4 | Sửa UI, Lấy dữ liệu sau khi add mới course
12 | User Access | User Login | iter1 | iter1 |  |  | - Log in to registered account | AnhNDHHE163634 | Done | II.1.a |  | not yet
13 | User Access | View Notifications | iter1 | iter1 |  |  | - Show Notifications | AnhNDHHE163634 | Done | II.2.c |  | not yet
14 | System Admin | New Program | iter2 | iter2 |  | x | -Create name route course , image , name route course 1 ,name route course 2 | DatNTHE161924 | Done | II.2.f |  | not yet | -Ảnh upload từ máy đã sửa UI
15 | System Admin | Program List | iter2 | iter2 |  | x | -Create name route course item , item route course introduction , choose route course and courses | DatNTHE161924 | Done | II.2.g |  | not yet | -Để dạng table , có ẩn hiện , để dạng buttom đã sửa UI
16 | User Access | Public Programs | iter2 | iter2 |  | x | - Load route course details | DatNTHE161924 | Done | II.1.p |  | not yet
17 | Web Blogs | Published Blog | iter2 | iter2 |  |  | - Load Blogs - Save Blogs - Change Pages | Daitvhe161138 | Done | II.1.l |  | not yet
18 | Web Blogs | Blog Details | iter2 | iter2 |  |  | - Add Blogs - Edit Blogs - Link written Blogs | Daitvhe161138 | Done | II.1.m |  | not yet
19 | Web Blogs | Blog View | iter2 | iter2 |  |  | - Like - Comment - Save Blog - View Blog | DungDTHE163862 | Done | II.1.k |  | iter4 | Like đã lưu chính xác vào bảng "LikeOfBlog" trong database
20 | Web Blogs | Written Blogs | iter2 | iter2 |  |  | - View published blog - Delete Blog | DungDTHE163862 | Done | II.1.j |  | iter4 | Slider đã include, không add trực tiếp vào page
21 | System Admin | Course List | iter2 | iter2 |  | x | - View published and unpublished courses | Trilmhe163206 | Done | II.1.n |  | iter4 | Sửa UI, Thêm isPulished, khi pulished thì mới show ra home page, nếu đã pulish thì không xóa được
22 | Web Blogs | Saved Blogs | iter2 | iter2 |  |  | - View saved blogs | Trilmhe163206 | Done | II.2.d |  | not yet
23 | User Access | Video Lesson | iter2 | iter2 | x |  | - Lessons are implemented through videos | AnhNDHHE163634 | Done | II.2.r |  | not yet
24 | User Access | Course Registration | iter2 | iter2 |  |  | - Register for courses that need to be paid | AnhNDHHE163634 | Doing | ii.2.s |  | not yet
25 | System Admin | Edit Program | iter3 | iter3 |  | x | -Edit name route course , image , name route course 1 ,name route course 2 | DatNTHE161924 | Done | ii.2.o |  | not yet | -Ảnh upload từ máy đã sửa UI
| User Access | Public Program Detail | iter3 | iter3 |  | x | -list each table of contents in each learning path | DatNTHE161924 | Done | II.1.p |  | not yet
| System Admin | Program Detail List | iter3 | iter3 |  | x | -list each table of contents in each learning route but you can edit, delete, add | DatNTHE161924 | Done | II.2.l |  | not yet | -Đã thêm filter, xóa phần giới thiệu đã sửa UI
28 | System Admin | New Route Course Item | iter3 | iter3 |  | x | -Edit name route course item , item route course introduction , choose route course and courses | DatNTHE161924 | Doing | II.2.r |  | not yet
29 | User Access | My Order | iter3 | iter3 |  |  | - Filter, search, cancel course | DungDTHE163862 | Done | II.1.t |  | not yet
30 | User Access | Q&A | iter3 | iter3 |  |  | - Make a question - Answer the question | DungDTHE163862 | Done | II.1.u |  | not yet
31 | System Admin | Course Edit | Iter3 | Iter3 | x |  | - Edit course details - Add, delete chapter - Add, delete description - Add, delete target - Add, delete requirement | Trilmhe163206 | Done | II.2.l |  | iter4 | Cho Target và Requirement vào textarea để tiện xử lí, sửa UI
32 | System Admin | Blog Management | Iter3 | Iter3 |  |  | - List Blog - Active/Unactive Blog - Filter Blog by name | Trilmhe163206 | Doing |  |  | not yet
33 | System Admin | Lesson Edit | Iter3 | Iter3 | x |  | - Edit type, url lesson | Trilmhe163206 | Done | II.2.n |  | iter4 | Sửa thành màn có chức năng show Lesson list, có thể filter theo các chương, Có thể xóa lesson
34 | System Admin | Chapter Edit | Iter3 | Iter3 |  |  | - Add, delete lesson | Trilmhe163206 | Done | II.2.m |  | iter4 | Sửa UI
35 | Learning Feature | Feedback Lesson | Iter3 | Iter3 |  |  | - View the survey - Answer the survey | Trilmhe163206 | Done | II.1.x |  | iter4 | Thêm phần cho người làm đánh giá sửa lại bản ghi
36 | User Access | My Course | Iter3 | Iter3 | x |  | - View my courses | Daitvhe161138 | Done | II.1.v |  | not yet
36 | System Admin | List QuizLesson | Iter3 | Iter3 | x |  | - List QuizLesson - Delete QuizLesson - Filter QuizLesson by Lesson | Daitvhe161138 | Done | II.2.i |  | not yet
38 | System Admin | New Quiz Lesson | Iter3 | Iter3 | x |  | - Add quiz lesson - Add answers - Add true answer | Daitvhe161138 | Done | II.2.j |  | not yet
| System Admin | Edit Quiz Lesson | Iter3 | Iter3 | x |  | - Edit quiz lesson | Daitvhe161138 | Done | II.2.k |  | not yet
40 | User Access | Quiz Lesson | Iter3 | Iter3 | x |  | - View quiz lesson - Choose answer - Show explain | Daitvhe161138 | Done | II.1.w |  | not yet
41 | System Admin | Comment Management | Iter3 | Iter3 |  |  | - Show Comment List - Show/Hide Comment | DungDTHE163862 | Done | II.2.h |  | iter4 | Filter/Search đã đảo sang trái
42 | User Access | See note in video lesson | Iter3 | Iter3 |  |  | - Show Comment in Video Lesson | AnhNDHHE163634 | Done | II.2.y |  | not yet
43 | User Access | Edit note in video lesson | Iter3 | Iter3 |  |  | - Change Comment - Delete Comment | AnhNDHHE163634 | Done | II.2.z |  | not yet
44 | System Admin | Edit Program Details | Iter4 | Iter4 |  | X | -This screen admin can change fields such as the name of the course table of contents, introduce the course table of contents and also change the courses. | DatNTHE161924 | Done | II.2.r |  | not yet
45 | System Admin | Course Route Management | Iter4 | Iter4 |  | X | -This screen will allow Admin to create route course , route course item , course,... | DatNTHE161924 | Done | II.2.e |  | not yet
46 | System Admin | List Quiz | Iter4 | Iter4 | X |  | -This screen will allow Admin to see a list of quizzes | Daitvhe161138 | Done | II.2.s |  | not yet
47 | System Admin | Edit Quiz | Iter4 | Iter4 | X |  | -This screen will allow Admin to add/remove questions from a quiz | Daitvhe161138 | Done | II.2.t |  | not yet
48 | User Access | Video Lesson | Iter4 | Iter4 | X |  | - Lessons are implemented through videos - Add note, delete note - See note | Trilmhe163206 | Done | II.1.s |  | not yet
49 | System Admin | Blog Management | Iter4 | Iter4 |  |  | - Show Blog List - Show/Hide Blog - Search, filter - Paging | Trilmhe163206 | Done | II.2.v |  | not yet
50 | System Admin | Edit Lesson Detail | Iter4 | Iter4 | X |  | - Edit details lesson - Change Chapter of Lesson | Trilmhe163206 | Done | II.2.u |  | not yet

## Iter1
# | Screen / Function | In Charge | Status | Notes
1 | Password Change | DatNTHE161924 | Done
2 | Password Reset | DatNTHE161924 | Done
3 | User Profile | DungDTHE163862 | Done
4 | Account Settings | DungDTHE163862 | Done
5 | User List | DungDTHE163862 | Done
6 | Home page | Daitvhe161138 | Done
7 | Public Courses | Daitvhe161138 | Done
8 | New course | Daitvhe161138 | Done
9 | User Register | Trilmhe163206 | Done
10 | Course Details | Trilmhe163206 | Done
11 | User Login | AnhNDHHE163634 | Done
12 | Notification | AnhNDHHE163634 | Done

## Iter2
# | Screen / Function | In Charge | Status | Notes
1 | Course Route Management | DatNTHE161924 | Done
2 | New Program | DatNTHE161924 | Done
3 | New Program Detail | DatNTHE161924 | Done
4 | Public Program | DatNTHE161924 | Done
5 | Public Program Detail | DatNTHE161924 | Doing
6 | Blog List | Daitvhe161138 | Done
7 | Blog Details | Daitvhe161138 | Done | Include add, edit Blog information, linked from written Blogs
8 | Blog View | DungDTHE163862 | Done
9 | Written Blogs | DungDTHE163862 | Done
10 | Course List | Trilmhe163206 | Done
11 | Course Edit | Trilmhe163206 | Doing
12 | Saved Blogs | Trilmhe163206 | Done
13 | Video Lesson | Trilmhe163206 | Done
14 | Course Registration | AnhNDHHE163634 | Done

## Iter3
# | Screen / Function | In Charge | Status | Notes
1 | My Course | Daitvhe161138 | Done
2 | List Question | Daitvhe161138 | Done
3 | New Question | Daitvhe161138 | Done
4 | Edit Question | Daitvhe161138 | Done
5 | Doing Quiz | Daitvhe161138 | Done
6 | Edit Program | DatNTHE161924 | Done
7 | New Program Detail | DatNTHE161924 | Done
8 | Program Details List | DatNTHE161924 | Done
9 | Public Program Detail | DatNTHE161924 | Done
10 | My Order | DungDTHE163862 | Done
11 | Q&A | DungDTHE163862 | Done
12 | Comment Management | DungDTHE163862 | Done
13 | Blog Management | Trilmhe163206 | Done
14 | Course Edit | Trilmhe163206 | Done
15 | Lesson Edit | Trilmhe163206 | Done
16 | Feedback Lesson | Trilmhe163206 | Done
17 | Chapter Edit | Trilmhe163206 | Done
18
19

## Iter4
# | Screen / Function | In Charge | Status | Notes
1 | Video Lesson | Trilmhe163206 | Done
2 | Blog Management | Trilmhe163206 | Done
3 | Edit Lesson Detail | Trilmhe163206 | Done
4 | List Quiz | Daitvhe161138 | Done
5 | Edit Quiz | Daitvhe161138 | Done
6 | Edit Program Details | DaiNTHE161924 | Done
7 | Course Route Management | DaiNTHE161924 | Done
8